# DCLT Communications Strategy

2025 Review & 2026–2029 Roadmap

# 2025: Foundation Year

First year focused on research, relationship-building, and infrastructure development. Visible deliverables (brand, website) are in progress; groundwork is laid for 2026 launch.

| Completed | In Progress |
| --- | --- |
| • Baseline public perception survey • Brand focus groups (community input) • Communications strategy documentation • Audience segmentation & personas • Preserve Explorer (near-complete) • Print appeals & playbill/newspaper ads • Development pipeline & best practices | • Brand identity (logo concepts ready) • Website architecture & custom blocks • New donation page flow |

# 2026–2029: Strategic Phases

| 2026 | 2027 | 2028 | 2029 |
| --- | --- | --- | --- |
| Brand & Website Launch | Engagement & Storytelling | Community Integration | Scale & Evaluate |
| • Logo & visual identity • Website launch • Design system • Email automation • Donation flow live | • "Humans of DCLT" • Working lands stories • Legacy giving program • Preserve signage • Donor segmentation | • IDEA initiatives • Educational programs • Partner expansion • Interactive content • Conservation Summit | • Impact assessment • 5-year campaign • Donor retention push • Next strategy plan • Final evaluation |

# 2026 Priority: Ship the Foundation

Everything else depends on brand and website. These are the proof-of-work that earns trust for future initiatives.

| Brand Launch Target: Q1 (Board presentation March) Logo + primary palette + typography Design system buildout to follow | Website Launch Target: Q2–Q3 New architecture, improved UX Donation flow, Preserve Explorer, SEO |
| --- | --- |

Door County Land Trust  •  Prepared December 2025